## Sheet1
Project Name: | Poblacion_ES_System_QA_Test_Project1
Prepared By: | Nathaniel Sales Duldulao
Date: | February 19, 2025 - June 16, 2025 (OJT Timeline 486hours)
Objective: | To perform manual and automation testing, including bug reporting, on all functionalities and the user interface of the Poblacion Elementary School System during its development phase as part of my OJT project, ensuring the system is free of bugs and fully functional.
Scope: | -Login: Default credentials only (admin/admin). -Student Registration: Add and edit student records; includes search functionality. -Data Management: Create, edit, and delete folders and files; includes search functionality.
Out of Scope: | -User roles other than default admin. -Advanced student features (grading, attendance, reports). -Features outside the development phase timeline.
Testing Approach: | -Manual Testing: Validation of all system functionalities and UI elements. -Automation Testing: For repetitive tasks such as regression testing using Cypress and JavaScript. -Bug Tracking: Document all identified issues using detailed bug reports, including steps to reproduce, severity, and status.
Tools Used: | Manual: Excel / Google Sheets Automation: Cypress + JavaScript Browser: Chrome and Firefox Tools: VSCode and Git/Github
Risk: | Browser compatibility (only tested in Chrome)
Schedule: | Test Design: June 2 – June 4, 2025 Test Execution: June 5 – June 10, 2025 Bug Reporting: June 11, 2025
Notes: | Bug reporting occurs simultaneously with test execution to ensure real-time documentation. Schedule includes buffer days to accommodate unexpected issues.